## Slide 1: Bug.sys
A fictional Subsidiary of polygames
Polygames is a fictional affiliate of Business Information Systems
BIS is a real program with Saskatchewan polytechnic

## Slide 2: Mission statement
To effectively manage projects that produce complete products of high quality using a consistent methodology and effective communication.

## Slide 3: motto
Process
Product
= Product++

## Slide 4: Our products

## Slide 5: Our Process
Planning
Executing
Controlling
Initiating
Closing
The initiation phase is where the project is approved, defined at a high level, and the stakeholders and teams are identified.
High level risk and reward decisions are made here and measured against feasibility
Questions:
Why do this?
What is the cost of doing nothing?
What does success look like?
What does failure look like?
Can we do it?
The planning phase is where we perform detailed planning on how we will execute the project. We determine exactly what the project is, how long it will take and how much it will cost.
Here we are concerned with scope & schedule (& budget).
Questions:
What are all the pieces of our project?
How long does each piece take?
Who will do what?
How will we monitor our project?
How and when will we communicate?
How will we handle change?
How will we handle risk?
Then we execute our plan. We monitor our progress, team morale, obstacles, risks. Communication is the key. The plan doesn’t have to be perfect – but communication does.
As we perform tasks, we reflect on the baseline plan. The goal is to identify variance early through scrums, status meetings, or informal communication.
Questions:
Are we on schedule?
Are we behind?
Are we ahead?
Were our estimates correct?
Is the team getting along?
Are the sponsors happy?
Answers to these questions help us control the project, which involves modifying the plan, and perhaps redefining what success look like.
Once the plan is revised the iterative cycle continues. Execute the new plan, control execution and adjust as required. At some point after success, failure or something in between, the project is formally closed.
A project is formally closed to ensure it is handed off to operations, to allow for a last round of team building, but most importantly to inform other projects of lessons learned along the way!

## Slide 6: Initiating
Planning
Executing
Controlling
Initiating
Closing

## Slide 7: Initiating
Planning
Executing
Controlling
Initiating
Closing

## Slide 8
Initiating
Identify the team
Establish the work space
Build the team
Who am I?
Co-location makes for more efficient teams
Who are we?
Team building starts in initiation, but is critical in every phase of the project
Self Identification form
Self directed team building activity
Deliverables:

## Slide 9
Initiating
What am I doing here?
I need to define my project
Request for Proposal (RFP)
Previous projects
Previous lessons learned reports
Assessment of your team
INPUTS:
Brainstorming session
Design discussion and form RFP response
Scope discussion and creation
ACTIVITIES:
RFP Response document
Scope document
DELIVERABLES:

## Slide 10
Getting your design approved may have additional steps:
Has another team already done it?
Is your scope clearly defined?
Is it too big (or too small)?
Do the sponsors think it can be done?
This feasibility analysis may include:
Locating tutorials
Gathering assets
Defining a smaller MVP
MINIMUM VIABLE PRODUCT
Using this to define success helps control scope and create a focus on quality.

## Slide 11
Good RFP Responses documents should:
Good scope statements should:
Be communicative
Identify similar products
Communicate value
Identify risks and concerns
Use visuals, sketches, screen shots
What inspired you?
How did you get your idea?
Why should we green light your project?
Why will the panel like your project
What seems hard?
What seems big?
What don’t we know?
Have a SMART goal
Accurately enumerate collections
“There will be enemy flies” 
“There will be 2 types of enemy flies”
Define the MVP
Have a healthy wish list
Identify meaningful scope exclusions
Specific, Measurable, Achievable, Realistic, and Timely
What was raised and abandoned?
What from the “Other project features” are we not doing?
These recommendations are outlined in the document templates provided.

## Slide 12
OK
You have the team
You have a product idea
You have sponsors who approve of the product
And you have consensus
Project Charter

## Slide 13
Consensus?
Achieved through communications
Captured through sign-off
Produces “alignment”
You’re all wrong!
“What if I don’t agree with the rest of the team?”

## Slide 14
Consensus doesn’t mean we all agree.
You’re all wrong!
Invalid
That is just stupid
I don’t want to do that
You don’t know what you’re doing
Valid
This can’t be done
We can’t do this
This seems risky
This is unprofessional
This is unethical/unfair

## Slide 15
Consensus doesn’t mean we all agree.
You’re all wrong!
Valid
This can’t be done
We can’t do this
This seems risky
This is unprofessional
This is unethical/unfair
Perform feasibility activities
Risk management
Request governance from sponsors

## Slide 16
Project Charter
Team and stakeholder contact info
Attendance and participation guidelines
Communication plan
Project time budget projections
Key dates (Milestones)
Team and sponsor signoff
Preliminary Risk
Game design and scope

## Slide 17
Time budget calculations
Calculate project capacity:
C = Total available hours from projected kickoff date to the presentation date.
H = Total available homework hours from projected kick off
L = Total lost hours due to projected potential absences
P = Planned absences (holidays, weddings etc.) calculated per individual
T = Team size
Capacity = (C + H - L) * T - P
INPUT
Attendance and participation guidelines
Information can be found in your document templates

## Slide 18
1-3 homework hours / week
Work over breaks?
Did you check holidays?
Lessons learned from past groups
Cross check with other groups
Time budget calculations

## Slide 19
Milestone List
Phase | Duration | Ideal Progression Date
Initiation | ~ 2 weeks | September 12
Planning | ~ 3 weeks | October 3
Execution | ~ 7 weeks | December 5
Closing | ~ 2 weeks | December 17

## Slide 20
DECEMBER 11
Revenge of
The Flytrap

## Slide 21: What next?
Break into your teams
Brainstorm a team name
  Must be submitted by end of first class
Review past material, discuss game idea
Access your team SharePoint