## Duration Worksheet
Duration Estimating Worksheet
Project Title: Forbidden Forest |  |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Class Days to Complete | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  |  | Team Member Name
1 Initiating Phase
1.1 Project Scope | 1.5 | 1.7 | 3 | 1.8833 |  | 1.8833 | 0.94167 |  | Brendan
1.2 Project Charter | 1.5 | 2 | 3 | 2.0833 |  | 2.0833 | 1.0417 |  | Osaro
1.3 Game proposal | 0.7 | 0.8 | 0.85 | 0.79167 |  | 0.79167 | 0.39583 |  | Osaro
1.4 Team Building Activity | 0.5 | 1 | 1.5 | 1 |  | 1 | 0.5 |  | Adriana
2 Planning Phase |  |  |  | 0 |  | 0
2.1 Risk analysis | 0.25 | 0.5 | 2 | 0.70833 |  | 0.70833 | 0.35417 |  | Team
2.2 Alpha Narrative | 0.3 | 0.4 | 2 | 0.65 |  | 0.65 | 0.325 |  | Osaro
2.3 Work breakdown structure | 1 | 1.2 | 1.5 | 1.2167 |  | 1.2167 | 0.60833 |  | Brendan
2.4 Project estimation | 1 | 1.2 | 1.5 | 1.2167 |  | 1.2167 | 0.60833 |  | Osaro
2.5 Project schedule | 1 | 1.2 | 1.5 | 1.2167 |  | 1.2167 | 0.60833 |  | Osaro
3 Executing Phase
3.1 Assets
3.1.1 Sprites | 35
3.1.1.1 Main Character | 5 | 10 | 15 | 10 |  | 10 | 5 |  | Andon
3.1.1.2 Enemy Spirte | 30 | 40 | 50 | 40 |  | 40 | 20 |  | Andon
3.1.1.3 Environment sprites | 3 | 4 | 5 | 4 |  | 4 | 2 |  | Brendan
3.1.2 Sound Effects | 3 | 3.5 | 4 | 3.5 |  | 3.5 | 1.75 |  | Osaro
3.1.2.1 Background music | 2 | 3 | 4 | 3 |  | 3 | 1.5 |  | Osaro
3.1.2.2 Enemy hit sound | 1 | 1.2 | 2 | 1.3 |  | 1.3 | 0.65 |  | Adriana
3.1.2.3 Spell Shoot sound | 1 | 1.2 | 2 | 1.3 |  | 1.3 | 0.65 |  | Adriana
3.2 GUI
3.2.1 Splash screen | 3 | 3.6 | 4.3 | 3.6167 |  | 3.6167 | 1.8083 |  | Osaro
3..2.2 Menu Scrren | 1.5 | 2.5 | 4 | 2.5833 |  | 2.5833 | 1.2917 |  | Osaro
3.2.3 Pause menu | 0.45 | 2 | 3 | 1.9083 |  | 1.9083 | 0.95417 |  | Osaro
3.2.4 Play button | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Osaro
3.2.5 High score button | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Osaro
3.2.6 Settings button | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Osaro
3.2.7 Credits button | 3 | 3.5 | 4 | 3.5 |  | 3.5 | 1.75 |  | Osaro
3.2.8 Quit button | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Osaro
3.3 Programming
3.3.1 Character
3.3.1.1 player movement | 4 | 6 | 8 | 6 |  | 6 | 3 |  | Brian
3.3.1.2 Player action buttons | 0.5 | 0.7 | 1.1 | 0.73333 |  | 0.73333 | 0.36667 |  | Brian
3.3.1.3 player weapon/spirite direction dynamics | 2 | 2.9 | 4 | 2.9333 |  | 2.9333 | 1.4667 |  | Brian
3.3.1.4 Player solid object dynamics | 2 | 4 | 6 | 4 |  | 4 | 2 |  | Brian
3.3.1.5 Player health | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Adriana
3.3.1.6 Ememy Health | 0.5 | 1 | 1 | 0.91667 |  | 0.91667 | 0.45833 |  | Adriana
3.3.1.7 Ememy spawn rate | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Brian
3.3.1.8 Enemy movement speed | 0.5 | 1 | 1 | 0.91667 |  | 0.91667 | 0.45833 |  | Brian
3.3.1.9 Enemy movement direction towards player | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Brian
3.3.2 Object
3.3.2.1 Player projectile collision | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Brian
3.3.2.2 projectile speed | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Brian
3.3.2.3 projectile damage | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Brian
3.3.2.4 map border | 1 | 2 | 3 | 2 |  | 2 | 1 |  | Brian
3.3.2.5 Weapon activation | 3 | 4 | 5 | 4 |  | 4 | 2 |  | Brian
3.3.3 Testing
3.3.3.1 Player Movement | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.2 Player action button | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.3 Player weapon/spirite direction dynamics | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.4 player solid object dynamics | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.5 Enemy solid object dynamics | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.6 Player health | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.7 Enemy health | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.8 Enemy spawn rate | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.9 Enemy movement speed | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.10 Enemy movement direction towards player | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.11 Player projectile collision | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.12 Enemy projectile collision | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.13 Projectile speed | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.14 Map border limits | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.15 Weapon Activation | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.16 Health bar | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.14 Pause game | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.18 Kill count | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.3.19 Help hover section | 0.5 | 1 | 2 | 1.0833 |  | 1.0833 | 0.54167 |  | Team
3.3.4 Miscellanous
3.3.4.1 Health bar | 2 | 1 | 4 | 1.6667 |  | 1.6667 | 0.83333 |  | Adriana
3.3.4.2 pause game | 2 | 3 | 4 | 3 |  | 3 | 1.5 |  | Adriana
3.3.4.3 kill count | 2 | 3 | 4 | 3 |  | 3 | 1.5 |  | Adriana
3.3.4.4 Help hover section | 2 | 3 | 4 | 3 |  | 3 | 1.5 |  | Adriana
4 Closing Phase
4.1 Individual Lesson learnt document | 0.3 | 0.4 | 0.5 | 0.4 |  | 0.4 | 0.2 |  | Team
4.2 GroupLesson learnt document | 12 | 13.5 | 14 | 13.3333 |  | 13.3333 | 6.6667 |  | Team
4.3 Peer evaluation | 0.75 | 1 | 1.25 | 1 |  | 1 | 0.5 |  | Team
4.4 Presentation | 1 | 1.1 | 1.2 | 1.1 |  | 1.1 | 0.55 |  | Team
Total Estimate | 171.125 | 148.6308 |  |  | Osaro | Brian | Adriana | Andon | Brendan | Team
Time Budget | 240 |  |  | Final Estimate Total | 32.0667 | 29.6667 | 20.2667 | 43.1083 | 32.1 | 36.0167
Slack Time | 68.875
ClayBar Studios