## Duration Worksheet
Duration Estimating Worksheet
Project Title: |  |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  | Team Member Name |  | Team Member Name |  | Team Member Name |  | Team Member Name |  | Team Member Name
Task 1 | 0.5 | 1 | 2 | 1.0833 | 1 | 2.0833 |  | 0.5 | 1.0417 | 1 | 2.0833 |  | 0 |  | 0 |  | 0
Task 2 | 0.5 | 1 | 2 | 1.0833 | 0 | 1.0833 |  | 1 | 1.0833 |  | 0 |  | 0 |  | 0 |  | 0
Task 2.1 | 1 | 1.5 | 4 | 1.8333 | 0 | 1.8333 |  | 1 | 1.8333 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | Total Estimate | 5 |  | 2.5 | 3.9583 | 1 | 2.0833 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Time Budget | 0
[5 empty] | Slack Time | -5 |  |  | 2.9167 |  | 0 |  | 0 |  | 0 |  | 0
Note on G9: Osborne, Gavin: Not sure about quality of tank sprite sheets on the Internet
Note on J9: Kopytko, Hannah: What percentage of this task is assigned to this this member. Smallest factor is .25
Note on K9: Kopytko, Hannah: Amount of time allocated to this member for this task based on the percentage of task assigned.