## Schedule v1.0
Gantt Chart | [71 empty] | % Complete (beyond plan)
[6 empty] | Period Highlight: | 59 | [30 empty] | Plan Duration | [5 empty] | Actual Start | [5 empty] | % Complete | [21 empty] | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION |  | PERCENT COMPLETE | PERIODS
[5 empty] | Resources |  | Nov | [15 empty] | Dec | [15 empty] | Jan | [17 empty] | Feb
[7 empty] | 7 | 7 | 9 | 9 | 14 | 14 | 16 | 16 | 21 | 21 | 23 | 23 | 28 | 28 | 30 | 30 | 5 | 5 | 7 | 7 | 12 | 12 | 14 | 14 | 19 | 19 | 21 | 21 | 26 | 26 | 28 | 28 | 2 | 2 | 4 | 4 | 9 | 9 | 11 | 11 | 16 | 16 | 18 | 18 | 23 | 23 | 25 | 25 | 30 | 30 | 1 | 1 | 6 | 6 | 8 | 8 | 13 | 13 | 15 | 15 | 16 | 16 | 20 | 20 | 22 | 22 | 27 | 27 | 29
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
Phase 1 - Project Management
1.1) Initiation Phase
1.1.1) RFP | 3 | 2 | 3 | 2 | all Dodgers | 100%
1.1.2) Project Charter | 4 | 3 | 4 | 3 | all Dodgers | 100%
1.1.3) Project Scope | 7 | 3 | 7 | 3 | all Dodgers | 100%
1.2) Planning Phase
1.2.1) Work Breakdown Structure | 9 | 4 | 9 | 4 | all Dodgers | 100%
1.2.2) Estimating Worksheet | 13 | 4 | 13 | 5 | all Dodgers | 80%
1.2.3) Project Schedule | 17 | 3 | 17 | 5 | all Dodgers | 70%
1.2.4) Risk Registry | 15 | 3 | 15 | 3 | Michael | 100%
1.2.5) Alpha Narrative | 19 | 2 | 19 | 3 | Shivalika | 100%
1.2.6) First Team Building Activity Documentation | 11 | 2 | 11 | 2 | Joy | 100%
1.3) Execution Phase
1.3.1) Change Log | 23 | 2 | 24 | 1 | all Dodgers | 100%
1.3.2) Issue Log | 23 | 2 | 24 | 1 | all Dodgers | 100%
1.3.3) Tracking Status Meeting Minutes (Alpha Meetings) | 47 | 2 | 47 | 1 | Michael, Namra | 100%
1.3.4) Tracking Status Meeting Minutes (Beta Meetings) | 61 | 2 |  |  | Shivalika
1.3.5) Second Team Building Activity Documentation | 51 | 2 | 57 | 2 | Joy | 100%
1.3.6) Create Kanban Board | 27 | 3 | 19 | 3 | Joy | 100%
1.4) Closing Phase
1.4.1) Individual Lessons Learned | 57 | 1 | 69 |  | all Dodgers
1.4.2) Group Lessons Learned | 58 | 1 | 69 |  | all Dodgers
1.4.3) Prepare Presentation | 53 | 4 | 67 | 3 | all Dodgers | 100%
1.4.4) Finalize SharePoint | 59 | 4 | 67 | 3 | all Dodgers | 100%
Phase 2 - Project Design and Development
2.1) Start Screen
2.1.1) Design
2.1.1.1) Develop Visual Layout | 23 | 2 | 24 | 1 | Namra | 100%
2.1.1.2) Collect Visual assets and soundeff ects | 25 | 3 | 25 | 1 | Namra | 100%
2.1.1.3) Create UML Diagram | 23 | 2 | 24 | 1 | Namra | 100%
2.1.2) Development
2.1.2.1) Code Start Screen Logic | 33 | 3 | 33 | 4 | Namra | 100%
2.1.2.2) Implement UI Functionality | 35 | 3 | 36 | 1 | Namra | 100%
2.1.3) Testing and Debugging
2.1.3.1) Conduct Unit Testing | 38 | 2 | 38 | 2 | Shivalika | 100%
2.1.3.2) Conduct Playtesting | 41 | 2 | 41 | 1 | all Dodgers | 100%
2.1.3.3 Debug and fix issues | 43 | 3 | 43 | 0 | Namra | 100%
2.2) Cultural Quotes Screen
2.2.1) Design Phase
2.2.1.1) Develop Visual Layout
2.2.2.1.1) Vietnamese | 23 | 2 | 23 | 2 | Joy | 100%
2.2.1.2.2) Indian | 33 | 2 | 28 | 2 | Joy | 100%
2.2.2.1.3) Igbo | 25 | 2 | 25 | 2 | Joy | 100%
2.2.2.1.4) Chinese | 49 | 2 | 28 | 2 | Joy | 100%
2.2.1.2) Collect Visual assets, sound effects and quotes
2.2.1.2.1) Vietnamese | 25 | 3 | 25 | 3 | Joy | 100%
2.2.1.2.2) Indian | 33 | 3 | 33 | 3 | Shivalika | 100%
2.2.1.2.3) Igbo | 31 | 3 | 31 | 3 | Joy | 100%
2.2.1.2.4) Chinese | 54 | 3 | 39 | 2 | Wei | 100%
2.2.1.3) Create UML Diagram | 23 | 2 | 23 | 2 | Joy | 100%
2.2.2) Development
2.2.2.1) Code Logic for displaying culturalquotes | 29 | 4 | 29 | 4 | Joy | 100%
2.2.2.2) Implement UI Functionality | 40 | 4 | 40 | 4 | Joy | 100%
2.2.3) Testing and Debugging
2.2.3.1) Conduct Unit Testing | 45 | 3 | 23 | 3 | Shivalika | 100%
2.2.3.2) Conduct Playtesting | 51 | 3 | 51 | 3 | all Dodgers | 100%
2.2.3.3) Debug and fix issues | 55 | 4 | 55 | 4 | Joy | 100%
2.3) Game Screens
2.3.1) Design Phase
2.3.1.1) Develop Visual Layout
2.3.2.1.1) Vietnamese | 23 | 2 | 23 | 2 | Michael, Wei | 100%
2.3.2.1.2) Indian | 25 | 2 | 25 | 2 | Joy, Shivalika | 100%
2.3.2.1.3) Igbo | 25 | 2 | 25 | 2 | Joy, Shivalika | 100%
2.3.2.1.4) Chinese | 49 | 2 | 49 | 2 | Joy, Shivalika | 100%
2.3.1.2) Collect Visual assets and sound effects
2.3.1.2.1) Vietnamese | 21 | 3 | 21 | 3 | Michael, Namra | 100%
2.3.1.2.2) Indian | 28 | 3 | 28 | 3 | Michael, Namra | 100%
2.3.1.2.3) Igbo | 33 | 3 | 33 | 3 | Joy, Michael | 100%
2.3.1.2.4) Chinese | 37 | 3 | 37 | 2 | Namra, Wei | 100%
2.3.1.3) Create UML Diagram | 23 | 4 | 23 | 2 | Michael, Wei | 100%
2.3.2) Development
2.3.2.1) Code Player Movements
2.3.2.1.1) Vietnamese (Level 1) | 27 | 4 | 25 | 4 | Michael | 100%
2.3.2.1.2) Indian | 51 | 2 | 41 | 1 | Michael | 100%
2.3.2.1.3) Igbo | 52 | 1 | 39 | 1 | Michael | 100%
2.3.2.1.4) Chinese | 53 | 1 | 39 | 1 | Wei | 100%
2.3.2.2) Implement Collision Detection
2.3.2.2.1)Vietnamese (Level 1) | 31 | 4 | 31 | 4 | Wei | 100%
2.3.2.2.2) Indian | 51 | 2 | 41 | 1 | Michael | 100%
2.3.2.2.3) Igbo | 52 | 1 | 39 | 1 | Michael | 100%
2.3.2.2.4) Chinese | 53 | 1 | 41 | 2 | Wei | 100%
2.3.2.3) Implement Falling Objects Logic
2.3.2.3.1) Vietnamese | 27 | 4 | 27 | 4 | Michael | 100%
2.3.2.3.2) Indian | 51 | 2 | 42 | 1 | Michael | 100%
2.3.2.3.3) Igbo | 52 | 1 | 40 | 1 | Michael | 100%
2.3.2.3.4) Chinese | 53 | 1 | 42 | 1 | Wei | 100%
2.3.2.4) Implement Cultural Items Logic
2.3.2.4.1) Vietnamese | 39 | 4 | 29 | 4 | Wei | 100%
2.3.2.4.2) Indian | 51 | 2 | 42 | 1 | Michael | 100%
2.3.2.4.3) Igbo | 53 | 1 | 39 | 1 | Michael | 100%
2.3.2.4.4) Chinese | 53 | 1 | 42 | 1 | Wei | 100%
2.3.2.5) Implement UI Functionality
2.3.2.5.1) Vietnamese | 27 | 4 | 27 | 4 | Michael, Wei | 100%
2.3.2.5.2) Indian | 37 | 3 | 42 | 3 | Michae | 100%
2.3.2.5.3) Igbo | 49 | 3 | 37 | 3 | Michael | 100%
2.3.2.5.4) Chinese | 55 | 3 | 39 | 2 | Wei | 100%
2.3.2.6) Code Top 5(Leaderboard) Logic
2.3.2.6.1) Vietnamese | 44 | 4 | 41 | 4 | Namra | 100%
2.3.2.6.2) Indian | 48 | 4 | 48 | 4 | Namra, Wei | 100%
2.3.2.6.3) Igbo | 52 | 3 | 52 | 2 | Namra | 100%
2.3.2.6.4) Chinese | 54 | 3 | 54 | 2 | Namra | 100%
2.3.3) Testing and Debugging
2.3.3.1) Unit Testing
2.3.3.1.1) Vietnamese | 35 | 3 | 35 | 3 | Shivalika | 100%
2.3.3.1.2) Indian | 55 | 2 | 55 | 2 | Shivalika | 100%
2.3.3.1.3) Igbo | 55 | 2 | 56 | 1 | Shivalika | 100%
2.3.3.1.4) Chinese | 55 | 2 | 59 | 1 | Namra | 100%
2.3.3.2) Playtesting
2.3.3.2.1) Vietnamese | 39 | 2 | 40 | 1 | all Dodgers | 100%
2.3.3.2.2) Indian | 57 | 2 | 53 | 1 | all Dodgers | 100%
2.3.3.2.3) Igbo | 57 | 2 | 54 | 1 | all Dodgers | 100%
2.3.3.2.4) Chinese | 57 | 2 | 54 | 1 | all Dodgers | 100%
2.3.3.3) Debug and fix issues
2.3.3.3.1) Vietnamese | 39 | 3 | 33 | 3 | Michael, Wei | 100%
2.3.3.3.2) Indian | 58 | 3 | 53 | 3 | Michael, Wei | 100%
2.3.3.3.3) Igbo | 59 | 3 | 47 | 3 | Michael, Wei | 100%
2.3.3.3.4) Chinese | 61 | 3 | 47 | 3 | Michael, Wei | 100%
2.4 End Screens
2.4.1) Top 5 Scenario Screen
2.4.1.1) Design Phase
2.4.1.1.1) Develop Visual Layout | 37 | 2 | 38 | 2 | Namra | 100%
2.4.1.1.2) Collect visual assets and sound effects | 38 | 2 | 35 | 1 | Namra,Wei | 100%
2.4.1.1.3) Create UML Diagram | 37 | 2 | 37 | 1 | Wei | 100%
2.4.1.2) Impalement UI Functionality
2.4.1.2.1) Display Player Points and leaderboard | 46 | 4 | 46 | 4 | Namra | 100%
2.4.1.2.2) Implement UI Functionality | 48 | 4 | 51 | 3 | Namra | 100%
2.4.1.3) Testing and Debugging
2.4.1.3.1) Unit Testing | 43 | 2 | 43 | 2 | Shivalika | 100%
2.4.1.3.2) Playtesting | 51 | 2 | 59 | 2 | all Dodgers | 100%
2.4.1.3.3) Debug and fix issues | 49 | 3 | 49 | 2 | Namra | 100%
2.4.2) Win Scenario Screen
2.4.2.1) Design Phase
2.4.2.1.1) Develop Visual Layout | 23 | 1 | 24 | 1 | Wei | 100%
2.4.2.1.2) Collect visual assets and sound effects | 25 | 2 | 26 | 1 | Wei | 100%
2.4.2.1.3) Create UML Diagram | 23 | 2 | 24 | 1 | Wei | 100%
2.4.2.2) Implement UI Functionality
2.4.2.2.1) Display Player Points and win message | 33 | 4 | 33 | 2 | Wei | 100%
2.4.2.2.2) Implement UI Functionality | 35 | 4 | 36 | 1 | Wei | 100%
2.4.2.3) Testing and Debugging
2.4.2.3.1) Unit Testing | 38 | 1 | 37 | 1 | Namra | 100%
2.4.2.3.2) Playtesting | 41 | 2 | 41 | 1 | all Dodgers | 100%
2.4.2.3.3) Debug and fix issues | 43 | 3 | 41 | 1 | Wei | 100%
2.4.3) Lose Scenario Screen
2.4.3.1) Design Phase
2.4.3.1.1) Develop Visual Layout | 23 | 1 | 23 | 1 | Wei | 100%
2.4.3.1.2) Collect visual assets and sound effects | 25 | 2 | 26 | 1 | Wei | 100%
2.4.3.1.3) Create UML Diagram | 23 | 2 | 24 | 1 | Wei | 100%
2.4.3.2) Implement UI Functionality
2.4.3.2.1) Display Player Points and lose message | 33 | 2 | 33 | 1 | Wei | 100%
2.4.3.2.2) Implement UI Functionality | 35 | 2 | 35 | 1 | Wei | 100%
2.4.3.3) Testing and Debugging
2.4.3.3.1) Unit Testing | 38 | 1 | 37 | 1 | Namra | 100%
2.4.3.3.2) Playtesting | 41 | 2 | 41 | 1 | all Dodgers | 100%
2.4.3.3.3) Debug and fix issues | 43 | 3 | 37 | 2 | Wei | 100%
2.5) Integration and Final Testing
2.5.1) Integrate Screens | 52 | 4 | 53 | 4 | Michael, Wei | 100%
2.5.2) Final gameplay testing and bug fixing | 63 | 4 | 57 | 10 | Michael, Wei | 100%
2.6) Deploy and Present Game
2.6.1) Deploy to platforms | 63 | 3 | 68 | 2 | Michael, Namra | 100%
2.6.2) Present game and documentations | 69 | 3 | 69 | 3 | all Dodgers | 100%
|  | 290 |  | 245
242
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please review gantt chart with elements dicussed in class, spcifically the amount of tasks on any given day and a more even spread of task across the timeline
Note on C3: hannah kopytko: The expected period you intend to start the task.
Note on D3: hannah kopytko: The excepted number of periods the task will take.
Note on E3: hannah kopytko: When the task is started, this should be filled in with the current period.
Note on F3: hannah kopytko: When the task is completed, this should be filled in with the number of periods it took to complete.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The person or people working on the task
Note on BI4: Fontaine, Joshua: Alpha
Note on I5: hannah kopytko: The date of the month this class falls on.
Note on BC5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Alpha Narrative Demo to Project Sponsors
Note on BQ5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta Demo to Project Sponsors; Project Should Be Fully Completed Before the Break
Note on I6: hannah kopytko: Represents 1 class hour, which is a single unit of time in our chart.
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Developing the visual layout for each culture also included implementing UI functionalities simultaneously.